## Tasks and Bugs
# | Project | Task Description | Type | Progress % | Note
1 | Dictionary | When the repository connection is stale, application crashes on any attempt to add, edit or remove a word | Bug | 50 | needs testing
2 | Dictionary | Automatically switch to SQL Repository, so I don't need to go switch manually. Create a config file where the last preference is stored | Feature | 100
3 | Dictionary | Have sort by type of the word | Feature | 100
4 | Dictionary | Color the words based on the type | Feature | 100
4.1 | Dictionary | Color the words based on the type in various languages | Feature | 70 | Works for English only
4.2 | Dictionary | Ability to turn on/off the coloring | Feature | 0
4.3 | Dictionary | Recolor the word if the wordtype changes | Bug | 0
5 | Dictionary | If you try to change the word type on SQL Repository it won't work. It is changed localy but not propagated to the databade. | Bug | 0
6 | Dictionary | Present user with a keyboard with the letters of the current language. This should be available as an option. | Feature | 100
7 | Dictionary | Create and Edit Languague | Feature | 70 | Only XMLRepository
8 | DictionaryTest | Create UI testing project with some tests | Test | 0
9 | DictionaryAndroid | Create an Android project for Dictionary | Feature | 0
10 | DictionaryIPhone | Create an iPhone project for Dictionary | Feature | 0
11 | TransliterationEditor | Count on number of rules and count on number of examples | Feature | 0
12 |  | Create a backup of the Dictionary SQL databade | Other | 0
13 | Transliterator | Make the algorithm take into account the CounterExamples such that the rule is not applicable for them | Feature | 0
14 | TransliterationEditor | Make search for rules | Feature | 0
15 | TransliterationEditor | Make search for examples | Feature | 0
16 | TransliteraitonEditor | Button "Reload and retest" should reload counter examples as they affect transliteraiton now | Bug | 0
17 | Transliterator | Deutsch: Sharp s and double s replace each other in the DB, so they can't coexist. | Bug | 0
18 | TransliterationEditor | Deleting examples crashes the app | Bug | 0
19 | TransliteraitonEditor | In examples introduce "distance" column which measures expected to transliterated distance | Feature | 0
20
21