## Tasks and Bugs
# | Project | Task Description | Type | Progress % | Note
1 | Dictionary | When the repository connection is stale, application crashes on any attempt to add, edit or remove a word | Bug | 0
2 | Dictionary | Automatically switch to SQL Repository, so I don't need to go switch manually. Create a config file where the last preference is stored | Feature | 0
3 | Dictionary | Have sort by type of the word | Feature | 100
4 | Dictionary | Color the words based on the type | Feature | 100
4.1 | Dictionary | Color the words based on the type in various languages | Feature | 70 | Works for English only
4.2 | Dictionary | Ability to turn on/off the coloring | Feature | 0
4.3 | Dictionary | Recolor the word if the wordtype changes | Bug | 0
5 | Dictionary | If you try to change the word type on SQL Repository it won't work. It is changed localy but not propagated to the databade. | Bug | 0
6 | Dictionary | Present user with a keyboard with the letters of the current language. This should be available as an option. | Feature | 100
7 | Dictionary | Create and Edit Languague | Feature | 70 | Only XMLRepository
8
9
10
11
12
13
14
15
16
17
18
19
20
21